## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
The OCR functionality for prescription extraction showed promising early results with good accuracy levels. Team cohesion was strong, allowing for effective brainstorming sessions. | Integrating AI validation processes proved more complex than expected, leading to delays in implementation. Some integrations with external databases faced unexpected compatibility issues. | Introduce iterative feedback loops for AI model updates to handle complexity. Establish a clearer documentation process for integration requirements. | Allocate dedicated time for AI model refinement in future sprints. Organize regular integration review meetings with the external teams. | Foster collaboration among all project stakeholders
The centralized inventory module design met initial requirements and is extensible for future needs. Team members shared valuable insights based on previous projects, enhancing development. | Time management regarding inventory tracking features fell short, affecting progress on other functionalities. Some team members faced challenges understanding the inventory model's complexity. | Break down the inventory module into smaller, manageable sub-tasks for clarity. Hold a knowledge-sharing session to clarify inventory management concepts. | Assign specific responsibilities for each inventory sub-task to streamline progress. Schedule knowledge sessions early in the sprint for better understanding. | Emphasize continuous learning and knowledge sharing
The integration of the pharmacy-specific chatbot began smoothly, with positive feedback on its initial capabilities. The demand forecasting component is taking shape with useful preliminary insights. | Unexpected bugs in the chatbot interactions delayed feature refinement. Data gathering for historical sales to inform forecast models was incomplete. | Incorporate a beta testing phase for the chatbot to gather user experiences. Prioritize completing data acquisition for forecasting to streamline further development. | Set aside time in the next sprint for user feedback on the chatbot. Identify and source missing historical sales data as an immediate priority. | Encourage iterative improvements based on user feedback
Stakeholder engagement during sprint reviews was high, allowing for immediate adjustments based on feedback. The early design of analytical dashboards showed valuable insights into sales trends. | Some operational metrics initially outlined proved difficult to capture effectively. Resource allocation for dashboard implementation was not as efficient as needed. | Simplify metrics by focusing on high-impact KPIs to improve reporting. Consider a phased approach to dashboard features for better resource management. | Create a prioritized list of KPIs for future development. Review team workloads regularly to ensure balanced resource distribution. | Focus on high-impact features for improved results