## Sheet1
Sprint Retrospective — Digital Pharmacy Management System
Sprint | What went well | What went poorly | What ideas do you have | How should we take action
Description | Successes and positive outcomes from the sprint. Practices that should be continued. | Challenges, roadblocks, or failures encountered. Areas that need improvement. | New approaches, tools, or strategies to enhance team efficiency and project outcomes. | Specific steps to address issues and implement ideas for continuous improvement. | Guidelines
Example
Sprint 1 (Dec 1–14) Setup & Planning | ✔ Full team alignment on project scope and technology stack achieved early. ✔ Database schema (4 tables: users, medicines, sales, prescriptions) designed and reviewed by both members. ✔ Development environment set up smoothly — no major configuration issues. ✔ GitHub repository created; branching strategy agreed upon. | ✘ Literature review took longer than estimated — research gap analysis spilled into Day 4. ✘ Initial architecture diagram had to be revised after team discussion on REST vs GraphQL. ✘ No clear definition of 'done' established for planning tasks. | 💡 Define acceptance criteria for every task before the sprint starts — not during. 💡 Timebox research tasks (2 days max) to prevent overrun. 💡 Create a shared architecture document on OneNote so both members can edit simultaneously. | → Jebin: Add acceptance criteria to all Sprint 2 Planner cards before Dec 15. → Thadhun: Set up shared OneNote architecture doc by Dec 15. → Both: Agree on Definition of Done at the start of every sprint going forward.
Sprint 2 (Dec 15–31) Backend & Database | ✔ All 6 backend API endpoints for inventory built and tested via Postman. ✔ JWT authentication with bcrypt password hashing implemented successfully. ✔ Role-based access control (ADMIN vs PHARMACIST) working end-to-end. ✔ PostgreSQL tables created via init.sql script — reproducible DB setup. | ✘ Database integration took an extra day due to connection pool configuration issues with pg library. ✘ API testing was done manually only — no automated test suite in place. ✘ Christmas holidays reduced productivity on Dec 25–26. | 💡 Write basic Jest/Supertest API tests for all endpoints to avoid regression bugs. 💡 Add a .env.example file to the repo so environment variables are documented. 💡 Use Postman Collections and export them to the repo for reproducible API testing. | → Jebin: Create Postman collection with all 6 API calls and export to repo by Jan 1. → Thadhun: Add .env.example with all required keys before Sprint 3 starts. → Both: Plan buffer days around public holidays in future sprint schedules.
Sprint 3 (Jan 1–14) Frontend Development | ✔ React + Vite frontend set up with working routing (React Router v6) and AuthContext. ✔ Dashboard, Inventory, and Sales pages all built and integrated with backend APIs. ✔ Role-based UI rendering working — Pharmacist sees view-only banner, Admin sees full CRUD. ✔ Chart.js bar chart for 7-day revenue trend integrated on Dashboard. | ✘ CORS errors blocked API calls for 2 hours on Day 7 — delayed integration. ✘ UI was not mobile-responsive; works only on desktop. ✘ No loading states on API calls — pages flash blank while data loads. | 💡 Add loading spinners and skeleton screens to improve perceived performance. 💡 Use Tailwind's responsive utilities (sm:, md:) to add basic mobile support. 💡 Create a frontend .env file for the API base URL so it is not hardcoded. | → Thadhun: Add loading spinner component reused across all pages in Sprint 4. → Jebin: Move API base URL to VITE_API_URL env variable before Sprint 4 starts. → Both: Test all pages on a mobile viewport before the final demo.
Sprint 4 (Jan 15–31) OCR Prescription | ✔ Google Gemini Vision API successfully integrated for prescription data extraction. ✔ Multer file upload module working — accepts JPG, PNG, PDF up to 10MB. ✔ Extracted JSON (patient name, medicines, dosages) saved correctly as JSONB in PostgreSQL. ✔ Prescription status tracking (Pending → Processed) implemented end-to-end. | ✘ Gemini API quota limit was hit during testing — caused 3-hour delay on Day 11. ✘ OCR accuracy dropped on handwritten prescriptions — printed prescriptions work much better. ✘ No error handling UI — if Gemini fails, the page just shows a blank response. | 💡 Add a retry mechanism with exponential backoff for Gemini API failures. 💡 Display a user-friendly error message and keep status as Pending if extraction fails. 💡 Add a manual override field so pharmacists can correct AI-extracted data. | → Jebin: Implement try/catch with friendly error toast in Prescriptions page in Sprint 6. → Thadhun: Add rate limit on the /upload endpoint (max 10 uploads per minute) in Sprint 6. → Both: Note OCR limitation for printed-only prescriptions in project documentation.
Sprint 5 (Feb 1–14) ML & Forecasting | ✔ Linear regression demand forecast implemented using simple-statistics library. ✔ 30-day synthetic sales data seeded via seedData.js for testing. ✔ 7-day forecast chart rendered correctly as a Chart.js line graph. ✔ Forecast API endpoint integrated cleanly with the Sales page frontend. | ✘ Model accuracy is low for medicines with fewer than 7 days of sales history. ✘ Feature engineering was simpler than planned — only date and quantity used. ✘ No model evaluation metrics (MAE, RMSE) tracked or displayed to the user. | 💡 Show a confidence indicator on the forecast chart (e.g., 'Low data — forecast may be inaccurate'). 💡 Add moving average as an alternative forecast method for comparison. 💡 Log MAE/RMSE values in the backend console for internal model evaluation. | → Thadhun: Add a warning banner on the forecast chart if sales history < 7 days in Sprint 6. → Jebin: Log MAE to backend console after each forecast call in Sprint 6. → Both: Document model limitations in the project report.
Sprint 6 (Feb 15–28) Chatbot & Integration | ✔ Gemini Chat API integrated with live inventory context — AI answers stock queries accurately. ✔ All 6 modules integrated successfully with no breaking cross-module bugs. ✔ End-to-end test passed: login → inventory → sale → prescription → forecast → chat. ✔ Project documentation and report completed on time. | ✘ Chatbot sometimes gives generic responses when inventory data is very large. ✘ System integration testing found 2 minor bugs (fixed same day) — ideally caught earlier. ✘ Documentation was left entirely to the last 2 days — caused a time crunch. | 💡 Truncate inventory context sent to Gemini — only send top 20 medicines by sales volume. 💡 Write integration tests progressively after each sprint rather than all at the end. 💡 Assign documentation tasks during the sprint, not after it ends. | → Jebin: Limit inventory context to top 20 medicines in the chatbot prompt for the final demo. → Thadhun: Prepare a demo script covering all 6 modules for the panel review. → Both: Archive the final codebase, report, and Planner board before the submission deadline.